| **ID** | **Name** | **Stakeholders** | **Action** | **Future Milestones** | **Due** |
| --- | --- | --- | --- | --- | --- |
| **Current Projects: Ongoing** | | | | | |
| EC1 | Research on key elements on Structural Reform | EC  SRMM | Liaise with EC to identify particular research topics |  | As required |
| EC4 | Voluntary reviews | EC  Participating Economies | Complete PSU role in assisting economies in undertaking reviews  Exploratory meeting with Indonesia’s MoF – 14 May 2010✓ | 2011 as required | As required |
| PSU1  PSU2 | StatsAPEC:   * Key Indicators Database * Bilateral Linkages Database | PSU Board  Member Economies | Release of StatsAPEC website✓  Optimization of StatsAPEC for mobile devices✓  Beginning 2011, biannual data updates:   * First update * Second update | 1 July 2010  August 2013  June 2017  December 2017 | Ongoing |
| PSU11 | PSU Policy Briefs | SOM  Member Economies | Release Policy Briefs that analyze pertinent policy relevant issues in the APEC region. | On needs basis | Ongoing |
| PSU27 | APEC in Charts 2017 | SOM  AMM AELM | Beginning 2013, annual publication for AMM | November 2017 | Ongoing |
| PSU28 | APEC Regional Trends Analysis | CTI EC  SOM  AMM | Beginning 2016, biannual reports:   * First report * Second report | May 2017  November 2017 | Ongoing |
| SOM16 | Support to APEC Services Competitiveness Roadmap | SOM  CTI GOS | Support development of services data & statistics to measure & support implementation of Roadmap; and work with fora responsible for carrying out APEC-wide actions to identify possible statistics to measure progress |  | Ongoing |
| **Current Projects: Discrete** | | | | | |
| CTI33 | Peer Review and Capacity Building on APEC Infrastructure Development and Investment (Reviewed Economy: The Philipppines) | CTI | Establishment of review team✓  Submission of Inception Report✓  Conduct document based review✓  Review visit✓  Submission of Progress Report✓  Submission of Draft Final Report  Submission of Final Report | 7 July 2016  November 2016  November 2016  December 2016  December 2016  February 2017  May 2017 | Q2 2017 |
| CTI34 | Facilitating Digital Trade for Inclusive Growth: Key Issues in Promoting Digital Trade in APEC | CTI | Project update at CTI2✓  Presentation at Trade Policy Dialogue and CTI3✓  Submission of Draft Report✓  Submission of Revised Draft Report✓  Submission of Final Report | May 2016  Mid-August 2016  October 2016  End-January 2017 March 2017 | Q1 2017 |
| CTI35 | Study on the Application of Global Data Standards (GDS) for Supply Chain Connectivity – Phase Two | CTI | Submission of Progress Report  Submission of Draft Final Report  Submission of Final Report | March 2017  May 2017  June 2017 | Q2 2017 |
| CTI36 | Case Study on Supporting Industry Promotion Policies in APEC – APEC Supporting Industry Initiative | CTI | Contractual negotiations & consultant appointment✓  Submission of Inception Report✓ Submission of Draft Report 1✓  Submission of Draft Report 2  Presentation of Draft Report 2 to CTI1  Submission of Draft Report 3  Submission of Final Report | Mid-November 2016  December 2016  End-January 2017  Mid-February 2017  End-February 2017  Mid-April 2017  May 2017 | Q2 2017 |
| CTI37 | Study on Single Window Systems’ (SWS) International Interoperability: Key Issues for its Implementation | CTI | Contractual negotiations & consultant appointment✓  Submission of Inception Report✓ Submission of Progress Report  Submission of Draft Final Report  Submission of Final Report | Mid-November 2016 December 2016  February 2017  May 2017  August 2017 | Q3 2017 |
| CTI38 | Promoting E-commerce to Globalize MSMEs | CTI | Project update to CTI3✓  Project update for CSOM✓  Project update to CTI1  Submission of Draft Report to CTI2  Submission of Draft Final Report to CTI3  Submission of Final Report | August 2016  October 2016  End-February 2017  May 2017  August 2017 October 2017 | Q4 2017 |
| CTI39 | Trends and Developments in Provisions and Outcomes of RTA/FTAs Implemented in 2016 by APEC Economies | CTI | Project update at CTI1 Submission of Draft Report for CTI2  Submission of Final Report for CTI3 | February 2017 May 2017  August 2017 | Q3 2017 |
| EC16 | Second APEC Ease of Doing Business Action Plan: Annual Progress Assessment 2016 | EC | Presentation of Preliminary Results at EC1  Submission of Draft Report  Submission of Final Report for EC2 | February 2017  June 2017  August 2017 | Q3 2017 |
| IEG2 | Investment Facilitation Action Plan (IFAP) Implementation Progress 2015-2016 | IEG | Submission of Draft Final Report to IEG1  Submission of Final Report | February 2017  April 2017 | Q2 2017 |
| PPWE2 | The APEC Women and the Economy Dashboard 2016 | PPWE  SOM | Submission of Draft Dashboard  Submission of Comments & Data by Economies  Submission of Final Dashboard | May 2017  June 2017  August 2017 | Q3 2017 |
| SOM15 | Partnerships for the Sustainable Development of Cities in APEC Region | SOM | Contractual negotiations & consultant appointment✓  Submission of Draft Final Report✓  Submission of Final Report✓ | 2 March 2015  12 January 2016  November 2016 | Q4 2016 |
| SCSC2 | Developing Indicators to Assess the Strength of Standards and Conformance (S&C) Infrastructure in APEC | SCSC | Contractual negotiations & consultant appointment✓  Submission of Inception Report✓  Submission of Progress Report 1 to SCSC1 Submission of Progress Report 2  Presentation of Draft Final Report to SCSC2  Submission of Final Report | 9 November 2016  December 2016  February 2017  June 2017  August 2017  October 2017 | Q4 2017 |
| **Completed Projects** | | | | | |
| CTI28 | Study on the Application of Global Data Standards (GDS) for Supply Chain Connectivity – Phase One | CTI | Report distributed – February 2017 |  | Done |
| GOS1 | Case Studies on the Role of Services Trade in Global Value Chains (GVCs) | GOS  MAG | Report distributed – February 2017 |  | Done |
| PSU11 | PSU Policy Briefs | SOM  Member Economies | [Trade of Fishery Products and Fisheries Subsidies in APEC (No. 16, January 2017)](http://publications.apec.org/publication-detail.php?pub_id=1805)  Accessed: 400 times  [Import Licensing Regimes: An APEC Snapshot and Considerations for their Use (No. 17, January 2017)](http://publications.apec.org/publication-detail.php?pub_id=1806)  Accessed: 400 times |  | Done |
| **Collaboration Matters** | | | | | |
|  | Increasing relationships with other international and research fora, and seeking to establish more formalized collaboration, possible joint research and information sharing arrangements where suitable | APEC, IMF, WB, ASEAN,  OECD, PECC, ERIA, ADB, etc. | Establish ongoing contacts with ADB, ADBI, ASEAN, ERIA, IMF, OECD, PECC, UNCTAD, WB, WEF, WTO, etc  Establish contacts with other organizations  Establish information sharing arrangements  Undertake joint work as appropriate and in the interests of APEC  Avoid duplication of effort | Ongoing | Ongoing |
| **Communication Matters** | | | | | |
|  | Research Outcomes: Summary of Research Projects 2016 | APEC Stakeholders | Beginning 2012, annual publication | Q2 2017 | Q2 2017 |
|  | Electronic mailer | APEC Stakeholders | Beginning 2012, electronic mailer for mailing list | Ongoing | Ongoing |
|  | Media activities | APEC Stakeholders | Prepare news releases  Participate in media interviews and briefings | Ongoing | Ongoing |
|  | PSU webpages | APEC Stakeholders | Maintain, update and improve contents in [PSU webpages](http://www.apec.org/About-Us/Policy-Support-Unit.aspx) | Ongoing | Ongoing |
|  | Speaking engagements | APEC Stakeholders | Participate in and speak at internal and external events | Ongoing | Ongoing |
| **Management Matters** | | | | | |
|  | Staff | PSU | Recruit staff and monitor performance  Manage workload of staff and consultants consistent with work program | Ongoing | Ongoing |
|  | Reports required by Governance Arrangements | PSU Board  SOM | Prepare a concise half-year evaluation report for the Board on work undertaken and expenditure and commitments  As soon as practicable after each calendar year, the PSU must submit to SOM an annual report on the PSU’s operations during the previous calendar year  The Board will regularly report the outcomes of its meetings to SOM  The PSU Director will regularly report on its activities to the Executive Director of the Secretariat | January and July to report on previous 6 month period  As soon as practicable after audit | Bi-annually  Annually  After each meeting  Ongoing |
|  | Mid-term review | PSU Board  SOM | Review the work and operations of the PSU and on the effectiveness of the PSU’s outputs from its establishment to 2016 and to provide recommendations for the strategic direction of the PSU | September 2016 – April 2017 | Q2 2017 |