| **ID** | **Name** | **Stakeholders** | **Action** | **Future Milestones** | **Due** |
| --- | --- | --- | --- | --- | --- |
| **Current Projects: Discrete** | | | | | |
| CTI54 | Assessment of Capacity Building Needs on Trade Related Aspects of E-commerce to Support WTO Negotiation on Trade Related Aspects of E-commerce | CTI | Submission of Inception/Progress Report✓  Submission of Interim Report✓  Submission of Draft Final Report  Submission of Final Report | 10 February 2020  30 June-14 July 2020 October 2020  November 2020 | Q4 2020 |
| CTI55 | Peer Review and Capacity Building on APEC Infrastructure Development and Investment (Reviewed Economy: Papua New Guinea) | CTI | Establishment of review team  Submission of Inception Report  Conduct document based review, interviews & review visits  Submission of Progress Report  Submission of Draft Final Report  Submission of Final Report | October 2020  End-October 2020  October 2020-May 2021  Mid-February 2021  Mid-June 2021  Early August 2021 | Q3 2021 |
| CTI57 | APEC Supply-Chain Connectivity Framework Action Plan 2017-2020 (SCFAP-II): Final Review | CTI | Submission of Inception Report  Submission of Progress Report  Submission of Draft Final Report  Submission of Final Report | February 2021  May 2021  August 2021  November 2021 | Q4 2021 |
| EC26 | Technical support to RAASR Action Team in preparation of input papers for 2020 Structural Reform Ministers’ Meeting | EC | Review TOR for consultants✓  Review proposal submission by consultants✓  Review first draft input papers✓  Review second draft input papers✓  Review final draft input papers✓ | December 2019  10 February 2020  4-15 April 2020  5-30 June 2020  September 2020 | Q3 2020 |
| EC27 | 2020 APEC Economic Policy Report (AEPR): Structural Reform and  Women’s Empowerment | EC | Consultant appointment✓  Submission of inception report✓  Economies to submit IERs & case studies✓  Submission of progress report✓  Submission of full draft of main report✓  Submission of final main report✓  Endorsement by EC  Submission to CSOM, AMM | 23 March 2020  10 April 2020  27 April 2020  29 May 2020  4 August 2020  31 August 2020  October 2020  November 2020 | Q4 2020 |
| EGILAT1 | Compendium of Resources for the Facilitation of the Trade and Distribution of Legally Harvested Forest Products in the APEC Region | EGILAT | Submission of Preliminary Report✓  Submission of Progress Report✓  Submission of Draft Final Report  Submission of Final Report | March 2020  August 2020  February 2021  August 2021 | Q3 2021 |
| SCE2 | APEC Case Studies on Inclusive Policies | SCE | Key Contributing Economies to submit case studies✓  Project Update at SCE1✓  Submission of Draft Case Studies✓  Submission of Final Case Studies to SCE3✓ | 8 October 2019-15 February 2020  18 February 2020  30 June 2020  11 September 2020 | Q3 2020 |
| SOM21 | Assessment of APEC Strategy for Strengthening Quality Growth | SOM AMM  AELM | Submission & presentation of draft assessment plan to SOM2✓  Submision of final assessment plan & questionnaires to SOM✓  Economies to submit completed questionnaires  Project Update✓  Submission of Draft Report✓  Submission of Final Report | 15-16 May 2019  15 July 2019  26 Sep 2019-15 March 2020  April 2020  31 August 2020  October 2020 | Q4 2020 |
| SOM22 | APEC Connectivity Blueprint: Mid-term Review | SOM  AMM | Submission & presentation of draft framework to SOM3✓  Submission of final framework to SOM✓  Request for comments on case studies & surveys✓  Economies to submit case studies & surveys  Submission of Preliminary Report✓  Submission of Draft Final Report✓  Submission of Final Report | August 2019  25 October 2019  14 February-18 April 2020  21 April-Mid-July 2020  14 July 2020  27 September 2020  November 2020 | Q4 2020 |
| SOM23 | APEC’s Bogor Goals: Final Assessment | CTI  SOM AMM | Economies to submit IAPs and fact sheet template  Preparation of First Draft Report✓  Submission of First Draft Report for review✓  Submission of Revised Draft Report to SOM✓  Submission of Final Report to CSOM | 27 March 2020  January-April 2020  25 April-22 May 2020  19 September 2020  November 2020 | Q4 2020 |
| **Current Projects: Ongoing** | | | | | |
| EC17 | RAASR sub-fund assessment group | EC | Beginning March 2017, participate as member to provide advice on concept notes | As required | As required |
| PSU1  PSU2 | StatsAPEC ([statistics.apec.org](http://statistics.apec.org/)):   * Key Indicators Database * Bilateral Linkages Database | Member Economies | Released July 2010; optimized for mobile devices 2013; reskinned 2020. Biannual data updates:   * First update✓ * Second update   News release: [Now Online: APEC’s Statistics Portal Gets a New Look](https://www.apec.org/Press/News-Releases/2020/0717_STATS) | June 2020  December 2020 | Ongoing |
| PSU11 | PSU Policy Briefs | Member Economies | Policy Briefs on pertinent policy relevant issues | On needs basis | Ongoing |
| PSU31 | APEC in Charts | SOM  AMM | Beginning 2013, annual publication for AMM | November 2020 | Ongoing |
| PSU32 | APEC Regional Trends Analysis | SOM  MRT  AMM | Beginning 2016, biannual reports:   * First report✓ * First report (update)✓ * Second report | May 2020  July 2020  November 2020 | Ongoing |
| SOM17 | Support to APEC Services Competitiveness Roadmap | GOS  CTI SOM | Support development of services data & statistics to measure & support implementation of Roadmap; and work with fora responsible for APEC-wide actions to identify possible statistics to measure progress | As required | 2025 |
| **Completed Projects** | | | | | |
| CTI52 | Trends & Developments in Provisions & Outcomes of RTA/FTAs Implemented in 2018 by APEC Economies | CTI | [Report distributed – March 2020](https://www.apec.org/Publications/2020/03/Trends-and-Developments-in-Provisions-and-Outcomes-of-RTA-FTAs-Implemented-in-2018-by-APEC-Economies)  Accessed: 1,550 times | - | Done |
| CTI56 | Technical Support for CTI’s Work on FTAAP Report to Leaders | CTI | Analysis submitted – August 2020 | - | Done |
| EC25 | Renewed APEC Agenda for Structural Reform (RAASR): 2016-2020 Final Review | EC | Report completed – September 2020 | - | Done |
| PSU11 | PSU Policy Briefs | Member Economies | [Do Public Capital Investments have an Impact on Economic Growth? (No. 29, January 2020)](https://www.apec.org/Publications/2020/01/Do-Public-Capital-Investments-Have-an-Impact-on-Economic-Growth)  Accessed: 1,600 times  [Circular Economy: Don’t let Waste go to Waste (No. 30, January 2020)](https://www.apec.org/Publications/2020/01/Circular-Economy---Dont-Let-Waste-Go-to-Waste)  Accessed: 2,640 times  [APEC in the Epicentre of COVID-19 (No. 31, April 2020)](https://www.apec.org/Publications/2020/04/APEC-in-the-Epicentre-of-COVID-19)  Accessed: 8,560 times  News release: [APEC Faces USD 2.1 Trillion in Output Loss to COVID-19](https://www.apec.org/Press/News-Releases/2020/0420_PSU)  Blog: [Preparing for the Next Pandemic](https://www.apec.org/Press/Blogs/2020/0427_COVID)  Video: [APEC Faces USD 2.1 Trillion in Output Loss to COVID-19](https://www.apec.org/Press/Videos/2020/0514_COVID-19) | Ongoing | Done |
|  |  |  | [Promoting Trade in Medical Products to Tackle COVID-19 Challenges (No. 32, April 2020)](https://www.apec.org/Publications/2020/04/Promoting-Trade-in-Medical-Goods-to-Tackle-COVID-19-Challenges) Accessed: 2,790 times  News release: [Promoting Trade in Medical Goods Will Save Lives](https://www.apec.org/Press/News-Releases/2020/0428_Healthcare)  Blogs: [COVID-19: Time to Lift Export Bans and Lower Barriers on Medical Goods](https://www.apec.org/Press/Blogs/2020/0421_COVID); [Through the Healthcare Barricade](https://www.apec.org/Press/Blogs/2020/0430_Healthcare)  Videos: [Promoting Trade in Medical Goods Will Save Lives](https://www.apec.org/Press/Videos/2020/0512_Carlos); [Medical Supplies and Personal Protective Products are Facing Barriers Worldwide](https://www.apec.org/Press/Videos/2020/0603_Medical)  [Export Restrictions and Food Security in the Context of the COVID-19 Pandemic](https://www.apec.org/Publications/2020/05/Export-Restrictions-and-Food-Security-in-the-Context-of-the-COVID-19-Pandemic) (No. 33, May 2020)  Accessed: 2,760 times  News release: [Safeguarding Food Security with Open Trade Policies](https://www.apec.org/Press/News-Releases/2020/0521_Food)  [COVID-19, 4IR and the Future of Work (No. 34, June 2020)](https://www.apec.org/Publications/2020/06/COVID-19-4IR-and-the-Future-of-Work)  Accessed: 6,560 times  News release: [COVID-19 Hastens Automation, New APEC Report Finds](https://www.apec.org/Press/News-Releases/2020/0626_Future)  Infographics: [COVID-19 and the Future of Work](https://www.apec.org/Press/Infographics/2020_0703_Info)  Blog: [COVID-19 altered the Future of Work](https://www.apec.org/Press/Blogs/2020/0703_Future)  [Supporting MSMEs’ Digitalization Amid COVID-19 (No. 35, July 2020)](https://www.apec.org/Publications/2020/07/Supporting-MSMEs-Digitalization-Amid-COVID-19)  Accessed: 4,290 times  News release: [As the Pandemic Pushes More Consumers Online, Small Businesses Need to Go Online](https://www.apec.org/Press/News-Releases/2020/0715_MSME)  Blog: [MSME Digitalization in the Time of COVID-19](https://www.apec.org/Press/Blogs/2020/0727_COVID)  Video: [Supporting MSMEs' Digitalization Amid COVID-19](https://www.apec.org/Press/Videos/2020/0727_MSMEs) |  |  |
| PSU32 | APEC Regional Trends Analysis | SOM  MRT  AMM | [May 2020: What Goes Around Comes Around: Pivoting to a Circular Economy; Uncertainty Tests APEC’s Resilience amid COVID-19](https://www.apec.org/Publications/2020/05/APEC-Regional-Trends-Analysis---What-Goes-Around-Comes-Around)  Accessed: 5,560 times  News release: [Trade and Economic Downturn Deepen Amid Tensions, Pandemic](https://www.apec.org/Press/News-Releases/2020/0527_ARTA)  Infographics: [Don’t Let Waste Go to Waste: Pivoting to a Circular Economy](https://www.apec.org/Press/Infographics/2020_0527_Dont-let-your-waste-go-to-waste); [Uncertainty Tests APEC’s Resilience Amid COVID-19](https://www.apec.org/Press/Infographics/2020_0527_APEC-Resilience-Amid-COVID)  Blogs: [COVID-19 and the Circular Economy](https://www.apec.org/Press/Blogs/2020/0528_COVID); [Towards a Greener “New Normal”](https://www.apec.org/Press/Blogs/2020/0616_Circular); [Rebuild Better](https://www.apec.org/Press/Blogs/2020/0629_COVID)  Video: [Pivoting to a Circular Economy](https://www.apec.org/Press/Videos/2020/0611_Circular-economy)  Virtual media briefing: [Latest updates on Economic and Trade Growth](https://www.apec.org/Press/Videos/2020/0604_ARTA)  [July 2020 Update: Deeper Contraction Calls for Decisive Action](https://www.apec.org/Publications/2020/07/APEC-Regional-Trends-Analysis-July-2020-Update)  Accessed: 4,610 times  News release: [COVID-19 Crisis Deepens Contraction in the APEC Region: Report](https://www.apec.org/Press/News-Releases/2020/0706_ARTA)  Infographics: [Uncertainty Tests APEC’s Resilience Amid COVID-19](https://www.apec.org/Press/Infographics/2020_0527_APEC-Resilience-Amid-COVID)  Video: [COVID-19 Impacts on Economy, Supply Chains & Businesses](https://www.apec.org/Press/Videos/2020/0702_COVID) | Ongoing | Done |
| SMEWG2 | Overview of the SME Sector in the APEC Region: Key Issues on Market Access and Internationalization | SMEWG | [Report distributed – April 2020](https://www.apec.org/Publications/2020/04/Overview-of-the-SME-Sector-in-the-APEC-Region)  Accessed: 1,620 times | - | Done |
| **Collaboration Matters** | | | | | |
|  | Establish relationships with other international & research fora, and more formalized collaboration, possible joint research and information sharing arrangements where suitable | - | Establish & maintain contacts with ADB, ADBI, ASEAN, ERIA, IMF, PECC, TAF, UNCTAD, UNESCAP, WB, WEF, WTO, etc  Establish information sharing arrangements & undertake joint work as appropriate  Implement PSU-OECD MOU 2018-2021 | Ongoing | Ongoing |
| **Communication Matters** | | | | | |
|  | Publications | - | Beginning 2012, annual publication of [Research Outcomes: Summary of Research Projects](https://www.apec.org/Publications/2020/07/Research-Outcomes---Summary-of-Research-Projects-2019)✓  Publication of PSU projects above | Ongoing | Ongoing |
|  | Outreach | - | Participate in internal/external events & briefings to visiting delegations; prepare electronic mailer | Ongoing | Ongoing |
|  | Online and social media | - | Maintain & update contents in [PSU webpages](http://www.apec.org/About-Us/Policy-Support-Unit.aspx)  Tap on APEC social media channels | Ongoing | Ongoing |
|  | Media activities | - | Prepare & contribute to news releases  Participate in media interviews & news briefings | Ongoing | Ongoing |
|  | Infographics and articles | - | Prepare & contribute to infographics, blogs and articles | Ongoing | Ongoing |
| **Management Matters** | | | | | |
|  | Staff | PSU | Recruit staff and monitor performance  Manage workload of staff & consultants consistent with work program | Ongoing | Ongoing |
|  | Reports required by Governance Arrangements | PSU Board  SOM | Prepare a concise half-year evaluation report for the Board on work undertaken and expenditure and commitments  As soon as practicable after each calendar year, the PSU must submit to SOM an annual report on the PSU’s operations during the previous calendar year  The Board will regularly report the outcomes of its meetings to SOM  The PSU Director will regularly report on its activities to the Executive Director of the Secretariat | January and July to report on previous 6 month period  As soon as practicable after audit  Ongoing  Ongoing | Bi-annually  Annually  After each meeting  Ongoing |