| **ID** | **Name** | **Stakeholders** | **Action** | **Future Milestones** | **Due** |
| --- | --- | --- | --- | --- | --- |
| **Current Projects: Discrete** |
| CTI42 | Bogor Goals Progress Report – IAP Peer Review Process 2018 | CTISOM | Submission of IAP Templates by members✓Preparation of Progress Reports✓Submission of Draft Progress Reports for review✓Discussion & Presentation of Draft Progress Reports✓Deadline for comments on Draft Progress Reports✓ Submission of Revised Progress Reports to SOM3✓ Submission of Final Reports to CSOM | 4 April 2018End-January-Mid May 2018Mid-May 201823-24 May 201813 June 20181 August 2018 November 2018  | Q4 2018  |
| CTI43 | Trends and Developments in Provisions and Outcomes of RTA/FTAs Implemented in 2017 by APEC Economies | CTI | Project update at CTI1✓Presentation of Draft Report to CTI3✓Submission of Draft Final Report to CTISubmission of Final Report  | 4-5 March 201814 August 2018September 2018October 2018  | Q4 2018 |
| CTI44 | Fostering an Enabling Policy and Regulatory Environment in APEC for Data-Utilizing Businesses | CTI | Submission of Inception Report✓ Submission of Progress Report to CTI3Submission of Interim Report Submission of Draft Final Report to CTI1 2019Submission of Final Report to CTI2 2019 | 15 June 2018Early September 2018Early November 2018Early February 2019Mid-April 2019 | Q2 2019 |
| CTI46 | Taking Forward the Lima Declaration on the Free Trade Area of Asia-Pacific (FTAAP) - Study on Tariffs | CTI | Submission of Progress Report 1 to CTI3 2018✓Submission of Progress Report 2 to CTI1 2019Submission of Progress Report 3 to CTI2 2019Submission of Final Synthesis Report to CTI3 2019 | 15-16 August 2018February 2019May 2019August 2019 | Q3 2019 |
| CTI47 | Peer Review and Capacity Building on APEC Infrastructure Development and Investment (Reviewed Economy: Indonesia) | CTI | Establishment of review teamSubmission of Inception ReportReview visitsConduct document based review & interviewsSubmission of Progress ReportSubmission of Draft Final Report Submission of Final Report | September 2018October 2018November 2018-June 2019November 2018-June 2019April 2019July 2019August 2019 | Q3 2019 |
| EC21 | 2018 APEC Economic Policy Report (AEPR): Structural Reform and Infrastructure | EC | Contractual negotiations & consultant appointment✓Literature review & data analysis for Parts 1 & 2✓Deadline for economies to submit IER & case studies✓ Review ABAC report✓ Synthesize IERs and review case studies✓ Submission of first draft of Parts 1 & 2 to Core Team✓Revision of first draft of Parts 1 & 2✓ Submission of final Parts 1 & 2 to Core Team✓Endorsement by EC, SFOMSubmission to CSOM, AMM | April 2018March-May 2018End-April 2018May 2018June 2018Mid-June 2018Early July 2018End-July 2018September,October 2018November 2018 | Q4 2018 |
| SOM17 | Case Studies on Addressing Connectivity Challenges in APEC Economies | SOM | Submission of Inception Report✓Submission of proposed case studies by members✓Project update at SOM2✓ Submission of Draft Progress Report at SOM3✓Submission of Draft Final Report at SOM3Submission of Final Report | 1 February 201830 April 201823-24 May 201814 August 2018September 2018November 2018 | Q4 2018 |
| SCE1 | Development and Integration of Remote Areas in the APEC Region | SCESOM | Interim report/update to SCE✓Submission of Draft Final Report to SCE✓ Presentation of Draft Final Report to SCE (SOM3)✓Submission of Final Report | 20 May 201824 July 201818 August 2018October 2018 | Q4 2018 |
| **Current Projects: Ongoing** |
| EC1 | Research on key elements on Structural Reform | EC SRMM | Liaise with EC to identify particular research topics | As required | As required |
| EC4 | Voluntary reviews | ECParticipating Economies | Assist economies in undertaking reviewsExploratory meeting - Indonesia MoF (14 May 2010)✓ | As required | As required |
| EC17 | RAASR sub-fund assessment group | EC | Beginning March 2017, participate as member to provide advice on concept notes  | As required | As required |
| PSU1 PSU2 | StatsAPEC:* Key Indicators Database
* Bilateral Linkages Database
 | Member Economies | Release of StatsAPEC website✓Optimization of StatsAPEC for mobile devices✓Beginning 2011, biannual data updates:* First update✓
* Second update
 | 1 July 2010August 2013June 2018December 2018 | Ongoing |
| PSU11 | PSU Policy Briefs | SOM Member Economies | Release Policy Briefs that analyze pertinent policy relevant issues in the APEC region.  | On needs basis | Ongoing |
| PSU27 | APEC in Charts 2018 | SOMAMM | Beginning 2013, annual publication for AMM | November 2018 | Ongoing |
| PSU28 | APEC Regional Trends Analysis  | CTIECSOMAMM | Beginning 2016, biannual reports:* [First report](https://www.apec.org/Publications/2018/05/APEC-Regional-Trends-Analysis)✓
* Second report
 | May 2018November 2018 | Ongoing |
| SOM16 | Support to APEC Services Competitiveness Roadmap | SOMCTIGOS | Support development of services data & statistics to measure & support implementation of Roadmap; and work with fora responsible for APEC-wide actions to identify possible statistics to measure progress | As required | 2025 |
| **Completed Projects** |
| CTI37 | Study on Single Window Systems’ (SWS) International Interoperability: Key Issues for its Implementation | CTI | [Report distributed – August 2018](https://www.apec.org/Publications/2018/08/Study-on-Single-Window-Systems-International-Interoperability)Accessed: 1,280 times  | - | Done |
| CTI41 | Peer Review and Capacity Building on APEC Infrastructure Development and Investment: Viet Nam | CTI | [Report distributed – May 2018](https://www.apec.org/Publications/2018/05/Peer-Review-and-Capacity-Building-on-APEC-Infrastructure-Development-and-Investment---Viet-Nam)Accessed: 620 times  | - | Done |
| CTI45 | Technical Support in preparing Report on Progress of FTAAP to Leaders | CTI | - | - | Done |
| CTI47 | APMEN assessment panel | CTI | Review Report on APMEN (Document No. 2018/SOM3/CTI/034)  | - | Done |
| EC19 | Mid-Term Review on Renewed APEC Agenda for Structural Reform (RAASR) | EC | [Report distributed – August 2018](https://www.apec.org/Publications/2018/08/RAASR-Mid-Term-Review-Report)Accessed: 470 times  | - | Done |
| EC20 | APEC’s Ease of Doing Business: Interim Assessment 2016-2017 | EC | [Report distributed – August 2018](https://www.apec.org/Publications/2018/08/APECs-Ease-of-Doing-Business)Accessed: 1,080 times | - | Done |
| PSU11 | PSU Policy Briefs | SOM Member Economies | [Identifying Green, Sustainable and Innovative MSMEs in APEC (No. 19, January 2018)](https://www.apec.org/Publications/2018/02/Identifying-Green-Sustainable-and-Innovative-MSMEs-in-APEC)Accessed: 3,920 times[Globalization, Inclusion, and E-Commerce: APEC Agenda for SMEs (No. 20, February 2018)](https://www.apec.org/Publications/2018/02/Globalization-Inclusion-and-E-Commerce---APEC-Agenda-for-SMEs)Accessed: 4,050 times[Services and the Food System (No. 21, May 2018)](https://www.apec.org/Publications/2018/05/Services-and-the-Food-System)Accessed: 1,450 times[Financing the Food Value Chain (No. 22, June 2018)](https://www.apec.org/Publications/2018/07/Policy-Brief---Financing-Food-Value-Chain)Accessed: 860 times | Ongoing | Done |
| PSU28 | APEC Regional Trends Analysis  | CTIECSOMAMM | [May 2018 Issue: Trade, Policy, and the Pursuit of Inclusion](https://www.apec.org/Publications/2018/05/APEC-Regional-Trends-Analysis) Accessed: 8,330 times  | Ongoing | Ongoing |
| SCSC2 | Developing Indicators to Assess the Strength of Standards and Conformance Infrastructure in APEC | SCSC | [Report distributed – April 2018](https://www.apec.org/Publications/2018/04/Developing-Indicators-to-Assess-the-Strength-of-Standards-and-Conformance-Infrastructure-in-APEC)Accessed: 2,450 times  | - | Done |
| **Collaboration Matters** |
|  | Increasing relationships with other international & research fora; seeking to establish more formalized collaboration, possible joint research & information sharing arrangements where suitable | ASEAN, ADB, ERIA, IMF, OECD, PECC, WB, etc. | Establish ongoing contacts with ADB, ADBI, ASEAN, ERIA, IMF, OECD, PECC, UNCTAD, WB, WEF, WTO, etcEstablish contacts & information sharing arrangements Undertake joint work as appropriate Avoid duplication of effort | Ongoing | Ongoing |
| **Communication Matters** |
|  | Research Outcomes: Summary of Research Projects 2017 | APEC Stakeholders | Beginning 2012, [annual publication](https://www.apec.org/Publications/2018/05/Research-Outcomes---Summary-of-Research-Projects-2017)✓Accessed: 2,480 times | Ongoing | Ongoing |
|  | Electronic mailer | APEC Stakeholders | Beginning 2012, electronic mailer for mailing list | Ongoing | Ongoing |
|  | Media activities | APEC Stakeholders | Prepare news releasesParticipate in media interviews and briefings | Ongoing | Ongoing |
|  | PSU webpages | APEC Stakeholders | Maintain, update & improve contents in [PSU webpages](http://www.apec.org/About-Us/Policy-Support-Unit.aspx) | Ongoing | Ongoing |
|  | Infographics | APEC Stakeholders | Develop infographics | Ongoing | Ongoing |
|  | Speaking engagements  | APEC Stakeholders | Participate in and speak at internal and external events  | Ongoing | Ongoing |
| **Management Matters** |
|  | Staff  | PSU | Recruit staff and monitor performance Manage workload of staff & consultants consistent with work program | Ongoing | Ongoing |
|  | Reports required by Governance Arrangements | PSU BoardSOM | Prepare a concise half-year evaluation report for the Board on work undertaken and expenditure and commitmentsAs soon as practicable after each calendar year, the PSU must submit to SOM an annual report on the PSU’s operations during the previous calendar yearThe Board will regularly report the outcomes of its meetings to SOMThe PSU Director will regularly report on its activities to the Executive Director of the Secretariat | January and July to report on previous 6 month periodAs soon as practicable after auditOngoingOngoing  | Bi-annuallyAnnuallyAfter each meetingOngoing |
|  | Performance Framework  | PSU Board  | Submission of Inception Report✓ Consultations✓Submission of Draft Report✓ Presentation to PSU Board✓Submission of Draft Final Report Finalization of Report  | 19 April 20184-8 June 20183 August 201818 August 2018September 2018October 2018 | Q4 2018 |