EWG 01/2009T

Reducing barriers to trade through development of a common protocol for measuring the seasonal energy efficiency (SEER) of air conditioners

Objective of the project

The objective of this project aims to develop an analytical platform to evaluate the SEER values of APEC member economies. This objective will be met based on the data of climate and building load characteristic collected from APEC economies. With the application of this program, it will help to reduce unnecessary duplicate test and administration process. Meanwhile, it also helps to reduce the cost and times of testing, and further affect the efficiency of trading among APEC economies.

Budget

The total approved budget for this study is US$60,000 from APEC funding.

Scope of Work

- Collect the weather data and the building load curve of the regions concerned.

- Develop a common code for performing Seasonal Energy Efficiency Ratio (SEER) of small air conditioners.

- Design and deliver one and a half days open workshop at Chinese Taipei on topic of air conditioning SEER to those experts or representatives mainly from APEC economies.

- Publish (consistent with APEC publication policy) and distribute 3 electronic copies of the outcome of workshop to workshop participants and others APEC Economies member.

- Provide an electronic copy of the above publications and the outcome of the development of SEER program to the APEC Secretariat for dissemination via the APEC Website.

Timetable & Deliverables for tenders

The proposed timetable for the completion of each stage of the project is as follows：

| Activities | Dates |
| --- | --- |
| Deadline for submission of proposals to the Project Overseer; | 30 April 2009 |
| Proposal evaluation and bid selection by Steering Committee of representatives from APEC Member Economies; | 1-6 May 2009 |
| Negotiation of contract details between the APEC Secretariat and the successful tender; | 7-15 May 2009 |
| Organization of workshop and invitation of speakers sent | 17 July 2009 |
| Stage 1 | 10 July 2009 |
| Planning overall SEER development structure Collection of information of related APEC economies weather data, consumer’s behavior of using air conditioner, building load characteristic and the existing regulation and standards |  |
| Finalized the details of workshop and complete lists of experts and participants | 28 August 2009 |
| Stage 2 | 25 September 2009 |
| Completion initial version of SEER program |  |
| Execution of Workshop; | 5-6 October 2009 |
| Publish and distribute the outcome of workshop to participants and others APEC Economies member. | 23 October 2009 |
| Stage 3 | 20 November 2009 |
| Complete the final version of SEER program with verified result |  |
| Collection result of workshop, SEER testing method and program | 4 December 2009 |
| Produce an electronic version of the above document for dissemination via the relevant APEC Websites. | 11 December 2009 |

Progress

- Complete the negotiation of contract details between the APEC Secretariat and the successful tender.

- Held the SEER Workshop. (Oct. 5-6)

- Complete initial version of SEER program.

Workshop for the Development of SEER

- A Workshop was held on Oct. 5-6 in conjunction with 34th EGEE&C in Taipei. The agenda of the workshop was as follows：

| First day – Seminar (5th Oct., 2009 / Mon.) |
| --- |
|  | Topic / Speaker |
| Venue | 4F/CR-403, The Howard Plaza Hotel Taipei, Taipei |
| 09:00 ~ 09:30 | Registration |
| 09:30 ~ 10:00 | Opening Remarks |
|  | Chair: Dr. Robert Yie-Zu Hu, Deputy General Director of Energy and Envirnment Research Laboratories, ITRI Co-Chair: Mr. Terry Collins, Chair of EGEE&C, APEC VIP Speech: Mr. Huey-Ching Yeh, Director General of the Bureau of Energy, MOEA, Chinese Taipei |
| 10:00 ~ 10:40 | Title: Policy and standards for the rational use of energy in Japan |
|  | Speaker: Dr. Chaobin Dang, Assistant Professor The University of Tokyo, Japan |
| 10:40 ~ 11:00 | Break |
| 11:00 ~ 11:40 | Tilte: CSPF & HSPF for air-conditioner and heat pump in Korea |
|  | Speaker: Dr. Jun-Young Choi, Chief Researcher Korea Testing Laboratory/Energy Technology Center, Republic of Korea |
| 11:40 ~ 13:10 | Lunch Break |
| 13:10 ~ 13:50 | Title: SEER for air conditioners in New Zealand |
|  | Speaker: Mr. Edward Winter MSc., Technical & Standards Advisor (Heating & Refrigeration), Energy Efficiency and Conservation Authority, New Zealand |
| 13:50 ~ 14:30 | Title: The Seasonal Energy Efficiency (SEER) of air conditioners in China standards |
|  | Speaker: Prof. Cheng Jianhong, Researcher China National Institute of Standardization, China |
| 14:30 ~ 14:50 | Break |
| 14:50 ~ 15:30 | Title: The role of SEER of air conditioner in energy efficiency management in Chinese Taipei |
|  | Speaker: Mr. Shin-Hang Lo, Manager Energy and Environment Research Laboratories, ITRI, Chinese Taipei |
| 15:30 ~ 16:10 | Title: SEER testing method and standard development in US |
|  | Speaker: Mr. Christopher G. Stone, General Manager Intertek, USA |
| 16:10 ~ 16:50 | Title: Establishment of the CNS national standards and development of SEER measuring method for air conditioners in Chinese Taipei |
|  | Speaker: Mr.Chwan-Shing Huang, Vice General Manager Research & Planning Department, Taiwan Electric Research & Testing Center, Chinese Taipei |
| 16:50 ~ 17:20 | Panel Discussion |

| Second Day – Panel Discussion (6th Oct., 2009 / Tue.) |
| --- |
| 09:30 ~ 10:10 | Title: The measures of promoting SEER for air conditioners from manufacturer's point of view |
|  | Speaker:Mr. Steve, R.C. Chang TRAEA, Chinese Taipei |
| 10:10 ~ 10:50 | Title: Introduction of the development of an analytical platform for measuring the SEER of air conditioners of APEC member economies |
|  | Speaker: Ms. Hsiao-Chi Hsu, Associate Researcher Industrial Technology Research Institute, Chinese Taipei |
| 10:50 ~ 11:10 | Break |
| 11:10 ~ 11:40 | Panel Discussion |
| End of Workshop |

- Experts invited were from 5 different economies, which were Japan, Korea, China, New Zealand, and USA.

| NO. | Economy | Name | Topic of presentation |
| --- | --- | --- | --- |
| 1 | New Zealand | Mr. Edward Winter MSc., Technical & Standards Advisor (Heating & Refrigeration), Energy Efficiency and Conservation Authority, New Zealand | SEER for Air Conditioners in New Zealand |
| 2 | Japan | Dr. Chaobin Dang Assistant Professor, The University of Tokyo | Policy and standards for the rational use of energy in Japan |
| 3 | China | Dr. Jianhong Cheng Researcher, China National Institute of Standardization | CSPF & HSPF for Air-conditioner and Heatpump in Korea |
| 4 | South Korea | Dr. Jun-Young Choi Chief Researcher, Korea Testing Laboratory/Energy Technology Center | The Seasonal Energy Efficiency (SEER) of Air Conditioners in China standards |
| 5 | USA | Christopher G. Stone | SEER testing method and standard development in US |

- Active participants invited were from 3 different economies：Russia, Malaysia and Indonesia.

| Active Participant | 1 | Russian Federation | Sergey Molodtsov Deputy Director on science, Centry for energy policy, Moscow |
| --- | --- | --- | --- |
|  | 2 | Malaysia | Zaini Abdul Wahab Demand Side Management, Energy Commission, Malaysia |
|  | 3 | Indonesia | Totok Sulistiyanto Vice President, ASHRAE Indonesia Chapter |

- The total number of participants is ***.

SEER Standards for APEC Economies

SEER program

- This program so far includes 6 economies’ standards (or drafts) about SEER.

- The 「User Define」 function is currently under construction. User can try different bin temp. V.S. bin hours to simulate the SEER value in different area.

- An electronic copy of the above publications and the outcome of the development of SEER program will be provided to the APEC Secretariat for dissemination via the APEC Website.