## Slide 1: EWG13 2012A Energy Saving Windows Thermal Performance Simulation Training Thailand
8 November 2012
EGEE&C 40
The Howard Plaza Hotel Taipei, Taipei

## Slide 2
Development of Energy Saving Window Thermal Performance Simulation Training
This workshop follows the success of the first one taken place in June 2011.
An activities towards the establishment of Building Materials Testing and Certification Center (BMTCC).
The workshop runs under the cooperation among 4 parties
  DEDE (Dr. Prasert Sinsukprasert)
  USDOE (Mark Le France and Cary Bloyd)
  US Consultant (Bipin Shah)
  KMUTT (Dr.Pattana Rakkwamsuk)
Proposal was submitted to APEC Secretariat Office in Singapore in June 2012 and a grant to run the workshop was awarded in mid of July 2012.

## Slide 3
In the proposal, responsible role
  Dr.Prasert (DEDE) is the project overseer
  Dr.Pattana (KMUTT) is responsible for organizing the workshop
A four-day workshop
  the first day will be arranged for a policy workshop
  the rest will be a window performance software training
The project costs USD $98,956.25
  Only USD 67,156.25 was requested from APEC (USD 19,000 for labour and hosting)
  The rest will be a self-funding
Project update

## Slide 4
Initially, the workshop was planned to be organized in September 2012. Unfortunately, we could not make it due to the fact that September was too soon by the time the proposal was approved.
We have rescheduled the workshop to some time in February.
Project update (Cont.)

## Slide 5
What is the status of the project?
In short, we can say:
DEDE has appointed KMUTT to organized the workshop.
The contract between APEC and KMUTT is being developed.
The workshop is expected to take place in February 2013.
Notes: By APEC Protocol, KMUTT, as a contractor appointed by DEDE, has to sign a contract with APEC.
In addition, APEC has to have a TOR for hiring KMUTT to to do the job. At the moment, I am drafting the TOR for Dr.Prasert to send it to APEC to develop the contract.