APEC Project Proposals:

Development Materials

November 2018

To be used with:

Guidebook on APEC Projects

(http://www.apec.org/Projects/Forms-and-Resources.aspx)

Contents:

- Model Proposals: some common features

- Background: the logic within your project

- APEC Quality Criteria for Assessing APEC Projects

- Proposal Writing Guide: Question by Question Tips

Please note: These materials provide a quick reference for Project Overseers (POs), forum members, APEC Secretariat staff and others interested in APEC project funding. This is a collection of resources that may assist in planning and writing a higher quality proposal. This package does not represent all guidelines, details or policies and may not be up-to-date with current guidelines. POs must follow the guidelines described in the most recent version of the Guidebook on APEC Projects. Please read this document in conjunction with the guidance note “2019: What do I need to know about the new Concept Note and Project Proposal” where you will find some sample Project Proposal responses. This document is in the PO Toolkit: https://www.apec.org/Projects/Forms-and-Resources Always ensure you are using the correct version of the Project Proposal. It is usually edited and re-published in October, after the second annual project session but well before the first project session of the new year. You will find the current version in the PO Toolkit. POs who would like further support or information should contact their forum’s Program Director (PD). The APEC Secretariat is available to assist with questions or challenges in the proposal development process. PDs, or a member of the Project Management Unit, may be able to assist you with more tailored and specific information. Download these and other resources from the APEC website: http://apec.org/Projects/Forms-and-Resources.aspx

Model Proposals: some common features

Model APEC proposals display some common features, regardless of which fora they have originated from, their funding source, or the proposing and co-sponsoring economies. Generally, model proposals:

- Are written in clear language with little technical jargon. Some readers may not be familiar with the field or issue.

- Provide a clear explanation of why the project is a priority for APEC.

- Show how the project is aligned with the eligibility criteria of the APEC funding source in question; and how the project supports the priorities of that funding source.

- Explain how the project will build capacity consistent with the Capacity Building Goals, Objectives and Principles of APEC.

- Establish a strong connection between the Outcomes planned for the project and the Objective of the project, and in turn, a connection between the Objective and  relevant APEC priorities and goals. Your project must be aligned with your forum’s work plan/strategic plan. Objectives must focused and targeted.

- Have clearly described Outputs, including a description of how they contribute to the project’s overall effectiveness. You can think of Outputs as the immediate results of the project’s work, or the activities that you do. They accrue during implementation.

- Establish a clear causal relationship between Outputs and Outcomes. Establish a clear alignment between the Outcomes and the project Objective.

- Map out the next steps that may be required after the completion of the project to ensure that the project’s positive work is sustainable.

- Explore the gender implications of the project, discussing how the project impacts women, or in female dominant sectors, men. Set quantifiable indicators to measure the success of project in meeting gender inclusiveness goals.

- Provide a clear timeline of all the actions and activities that will happen in the project from beginning to completion.

- Take stock of the current situation in order to establish a baseline that can be used to monitor and evaluate the effectiveness of the project.

- Define clear and quantifiable indicators which can be used to measure the extent to which the project has delivered all the outputs and achieved all the planned outcomes; both as the project progresses, and at the end of the project.

- Outline the consultation and collaboration with other APEC fora and relevant external organizations. This collaboration should add value, reduce costs and expand the area of influence for the project.

- Explain, in concrete terms, how the project adds to work already completed and builds on previous findings and lessons learned.

- Explain the APEC “value-added”, or why APEC is the best organization to fund the project, rather than another organization.

- Present an accurate and considered budget that is compliant with APEC funding entitlements and restrictions.

Background – the logic within your project

Projects are a vital part of the APEC process. It is important that projects are both thoroughly planned and managed, to ensure they achieve their intended project outcomes and meet their overall objectives. Projects in APEC are based on a simple underlying ‘program logic’ that reflects a causal chain between the project’s outputs (or activities), the project’s outcomes, and the overall project objectives. These are all collectively resourced by the project’s budget. Stating the project outputs (e.g. a workshop, a best-practices guidebook, a summary report) can be a straightforward task. But defining a set of project level outcomes can be a more challenging task. POs should be careful to avoid confusing a project’s outputs with a project’s outcomes and further, care should be taken to avoid confusing the outcomes with the project’s objective(s). The program logic in your project doesn’t need to be complex. Most projects are 1-2 years in duration with a small set of outcomes linked to 2-3 outputs.

To explain the causal chain, see below:

OBJECTIVE The OBJECTIVE is the overarching goal, purpose, or intention, of your project. You can have multiple objectives but you should be realistic. Be careful to avoid describe objectives which are actually outcomes. OUTCOMES OUTCOMES are the changes, impacts or benefits that your project generates. The outcomes are what happens when you successfully deliver your outputs as planned Outputs make outcomes happen, that is, they are linked by a causal relationship. Outcomes need to be measurable and must be attributable to your project. Your outcomes must align with, and support your project objective. The success of your project depends on whether you have achieved the planned outcomes and as a result, fulfilled the project objective. OUTPUTS OUTPUTS are the activities undertaken within a project, or the products of a project, which are undertaken or created to achieve the outcomes. Measuring outputs is usually straightforward: number of attendees at a workshop, services delivered on time, numbers of speakers, gender disaggregation; etc. PROJECT BUDGET The project budget describes the resource that support your project.

APEC Quality Criteria for Assessing APEC Projects

APEC assesses project quality using five criteria.  The following questions form the basis of the quality assessment and are useful to ask yourself while preparing your proposal and developing your design. For more information please refer to Appendix D of the Guidebook.

| Relevance | This looks at WHY a project is proposed. Relevance considers the extent to which projects are needed and suited to achieving the priorities and objectives of the target group, the recipient member economies and APEC as a whole. APEC Committee work plans and sub-fora Working Group plans are an important reference point for what is relevant to a group’s priorities. - How valid is the objective of the project? - Are the activities and outputs of the project consistent with the planned project outcomes? - Are the activities and outputs of the project consistent with the project objective? |
| --- | --- |
| Impact (Project Level) | This asks WHAT the project seeks to change. It includes possible impacts on key stakeholders and effectiveness in addressing APEC values such as gender equity. Impact will consider project risks and risk management, including the possible impact of external factors, such as changes in terms of trade or financial conditions. - What are the likely changes following from this project? - What difference will the activity make to the target beneficiaries? - Beyond the target group, who else is likely to benefit? Are there multiplier effects that can be gained from this project? - What support exists for the project across APEC, taking into account the potential for multiple fora support to reinforce the benefits across a range of sectors and areas of work? - What avenues will be used to communicate and promote the project results, not only to member economies but also stakeholders and desired partners? |
| Effectiveness | This examines HOW a project will take place, particularly how well a project might achieve its outcomes and reach the objective. - To what extent are the outcomes likely to be achieved and are they realistic? - What is the APEC value-add? Why is this a good project for APEC? - Based on the particular issue being addressed, is the proposed approach a sound way to achieve the outcomes, and have other alternative approaches been examined? - Does the project take into account and or build on previous APEC activities with a similar objective? |
| Sustainability (Project level) | This looks at whether the benefits of a project are likely to continue after the APEC project is completed. It has a longer term focus compared to other criterion. - What are the intended effects over the longer term? - Does the project provide for methods to ensure benefits of a project will continue after the APEC project ceases? - Is there evidence of engagement with key stakeholders? - How does this project fit in with fora’s priorities and are follow-on projects planned? |
| Efficiency | This also looks at HOW a project will take place, particularly measuring of the outputs (services, goods) in relation to the inputs (cost of resources). Efficiency considers if the project offers value for money and whether projects use the least costly resources allowed in order to achieve the desired results. - Do the activities appear to be cost-efficient? - Do the activities comply with APEC project budget guidelines? - Would alternative approaches deliver the same result for less cost? |

Proposal Writing Guide: Question by Question Tips

Shaded sections contain useful tips and advice, but this document is a resource only.

All projects must be developed using the most recent version of the Guidebook on APEC Projects.

| Project title and number: |  |  |  |
| --- | --- | --- | --- |
| Fund Source (Select one): General Project Account (GPA) Trade and Investment Liberalization and Facilitation Special Account (TILF) APEC Support Fund (ASF) – General Fund APEC Support Fund (ASF) – Sub-Fund*. You must nominate the sub-fund here: ……………………… |  |  |  |
| APEC forum: |  |  |  |
| Proposing APEC economy: |  |  |  |
| Co-sponsoring economies: |  |  |  |
| Expected start date: | The minimum applicable amount of co-sponsors must be confirmed before the Internal Submission Deadline. APEC processes require a minimum of two co-sponsors, but individual groups may have other requirements, so check with your Program Director. |  |  |
| Project Completion Date: See Chapter 7 Guidebook on APEC Projects | Projects selected in the first project session of 2019 will have a standard project completion date (PCD) of 31 December 2020. Projects selected in the second 2019 project session will have a standard PCD of 30 June 2021. Earlier PCDs are subject to Secretariat approval. |  |  |
| - Project summary: - In 150 words - - What is the issue that you will address or examine in your project? - Outline the key things your project will do, in terms of what, where, when and with whom. - (Summary must be no longer than the box provided. Cover sheet must fit on one page) | Copy this part over from the Concept Note |  |  |
| Summary of Proposed Budget (USD) : | APEC funding | Self-funding | Total |

Project Overseer Information and Declaration:

Name:

Title:

Organization:

Postal address:

Tel:       	      E-mail:

As Project Overseer and on behalf of the above said Organization, I declare that this submission was prepared in accordance with the Guidebook on APEC Projects and any ensuing project will comply with said Guidebook. Failure to do so may result in the BMC denying or revoking funding and/or project approval. I understand that any funds approved are granted on the basis of the information in the document’s budget table, in the case of any inconsistencies within the document.

Name of Project Overseer / Date

Project Details

The overall proposal including the title page and budget should be 12 pages or less. Remember that the reviewer may not be familiar with your sector, so keep your language simple. The information in questions 1, 2, 3, 6, 9, 11, and 12 can be taken or adapted from the Concept Note. You may make adjustments as required, or provide a greater level of detail, but your answers should essentially reflect what you proposed at the Concept Note stage. If you are making any substantive changes to your Concept Note responses, you need to clearly highlight these in your proposal and explain your reasons. Endorsement: The proposal must be endorsed by the relevant forum before it can be reviewed by the Secretariat against the Quality Indicators. Please submit your draft Project Proposal to your Program Director on or before the date identified for submission, so your Project Proposal can be circulated for endorsement, including reviews and co-endorsement by other fora where stipulated by the eligibility criteria of specific APEC project funding sources.

SECTION A:  Relevance to APEC

[Answers to questions 1–3 may be taken or adapted from the Concept Note]

- Relevance: What problem does the project seek to address? Does it have sustained benefits for more than one economy?

Relevance – Eligibility: How does the project a) meet the eligibility criteria and b) support the funding priorities for the nominated fund or sub-fund?

Relevance – Capacity Building: How will the project build the capacity of APEC member economies. For ASF projects, please identify the APEC developing member economies that will benefit from this project. (Refer to capacity building goals, objectives and principles at Appendix K of the Guidebook.) [½ page]

Combine your responses from the Relevance sections in your Concept Note here. This response should convince the reviewer that your project is vital to the interests of APEC economies. In your description of the problem (or opportunity) that needs to be addressed, you may include: - How the problem/opportunity affects APEC economies and/or certain sectors. - An overview of how your project will improve conditions for these economies/sectors. - The current status of the issue in APEC or in the broader international community. - How the project will benefit multiple APEC economies beyond the proposing economy. - How the project meets the eligibility criteria and the specific priorities of the nominated APEC funding source. - How the project will build capacity. Capacity building is central to APEC Projects. When completed, your project should have improved the enabling environment for APEC economies to deliver against APEC’s agreed priorities and goals. Your project will do this by including well-designed activities which increase the capacity of participants, and their respective institutions, to play a positive contributory role within this enabling environment. Further information on capacity building in APEC can be found in the Guidebook. Note that all ASF projects must address capacity building, and benefit at least one developing APEC economy.

- Objectives: State the overall objective of the project in 100 words or less (refer to your Concept Note).

Copy this part over from the Concept Note

- Alignment-APEC:  Describe specific APEC priorities, goals, strategies, and/ or statements that the project supports, and explain how the project will contribute to their achievement.

- Alignment-Forum: How does the project align with your forum’s work plan / strategic plan?  [½ page]

You may combine your responses from both Alignment sections in your Concept Note here. How does the project and its objectives align with APEC’s current priorities and goals? - Mention specific APEC priority goals, leaders’ statements, ministerial statements, strategies, action plans, initiatives, etc. - Cite any connection with previous or planned activities, in any work plan approved by Leaders, Ministers, and Committees. - Describe the elements of your Committee/fora’s workplan that the project aligns with. Describe how and why your project is the obvious next step.

SECTION B:  Project Impact

- Outputs: Using a numbered list in chronological sequence, identify the key products or services that will happen during the implementation of your project in support of the outcomes. This may include workshops, reports, analytical inputs, research work, recommendations, best practice guidelines, action plans, websites etc. Be brief but describe key parameters, like purpose, duration, location, expected scope and scale, timelines etc. [½ to ¾ page]

Outputs are essentially the key activities within your project. Outputs are the things that need to happen to make your outcomes happen. They might include: - Events: workshops, seminars, conference (most effective events then achieve further outputs, such as creating tools, drafting recommendations, agreeing on an action plan etc., as below) - Tools: recommendations, a set of best practices, analytical frameworks, action plans - Knowledge: a research paper, survey results, an analytical report, improved abilities in a particular area - Collaboration: standards, agreements, identification of next steps, networking opportunities etc. List the Outputs in the chronological order they will be delivered. Describe them with a short title and use that title consistently throughout the Project Proposal, using capitals (e.g. Initial Project Seminar). Describe them in detailed terms, and also describe any supporting activities. You may also describe the benefits that the Output is creating for participants/beneficiaries. Focus on benefits that can be directly attributed to your project. Consult the PO Toolkit document “2019: What do I need to know about the new Concept Note and Project Proposal” for an example response.

- Outcomes: Using a numbered list, describe the specific impacts, changes or benefits that the project is expected to deliver, which directly support the project objective (above). These include changes in policy, processes, or behaviour in the participating institutions, or in APEC more broadly. Be sure that each outcome can be measured and is a direct result of the project. [½ to ¾ page]

The outcomes that your project generates are the changes, impacts or benefits that you plan to flow from the delivery of your outputs. Outcomes happen as a consequence of your project, so they are best expressed in the past tense, for example, ‘practice guidelines implemented’ or ‘enhanced policies adopted’. Your project outcomes must support your stated project objective(s). Place your outcomes in a numbered list so they are clear. The outcomes must be dependent on your project, meaning that they occur because your project happened. Avoid outcomes which are too high level as it may be hard to demonstrate a direct to link to your project. Each outcome must be accompanied by at least one indicator, which you use to assess whether or not you have achieved the outcome. Don’t rely solely on indicators which just record the physical aspects of outputs, like simply counting the people attending a workshop. Alternatively, you could measure the degree to which participants knowledge levels were increased as a result of your workshop. Because your indicators measure change, or impact, it is vital that you understand the starting point or baseline before your project. You could, for example, survey levels of participant knowledge before the workshop. You could also undertake research to understand the ‘state-of-play’ before your project, such as doing a survey, desk research or other information gathering work. Once you understand the baseline situation, you can then describe what level of change your project is targeting. Your indicator can then be used to measure if this target has been reached or not. It is feasible that some project outcomes, or elements of project outcomes, occur after the formal completion of your project. If that is the case, you need to make this clear in the Project Proposal and Completion Report, and you need to explain how you will continue to monitor and evaluate that outcome after the end of the project. You can report back to the Secretariat after the project, or use the annual Longer-Term Evaluation of APEC Projects as an opportunity to report further progress. Consult the PO Toolkit document “2019: What do I need to know about the new Concept Note and Project Proposal” for an example response.

- Beneficiaries: Who are the direct project participants and users of the outputs? Describe their qualifications, level of expertise, roles/level of responsibility, gender, economies represented, government departments, APEC fora involvement etc. Explain how they will use and benefit from the project. Who else will benefit from the project and how? [½ to ¾ page]

Describe in this section the Direct Beneficiaries and identify any Long-Term or Indirect Beneficiaries. Direct Beneficiaries are the people who will experience the project (e.g. workshop participants, policymakers using the tool created etc.) and use the outputs of the project (workshop, report, research results etc.) in an immediate way. Focus your project discussion on these people. Long-Term or Indirect Beneficiaries: Limit your focus on this group if they will benefit only after the project is over and/or only if next steps are followed. Conversely, highlight benefits to the general public or end consumers if the project plans to provide them with longer term benefits such as reduced prices, better product quality, etc. Use this section to identify women or groups of women who will benefit from this project.

- Dissemination: Describe plans to disseminate results and/or outputs of the project, including:

- The number, form and content of any publications. (Note: APEC will not fund publications that are only presentation slides, or website maintenance. Electronic publication encouraged.)

- The target audience.

- Any intention to sell outputs arising from this project.        		[less than ½ page]

Publications may include curricula, statistical studies, web content, CDs, electronic documents, hard-copy reports, etc. All APEC publications must meet the relevant guidelines. Draft publications will be reviewed by the APEC Secretariat before publication. Ensure that draft publications do not require any further copy-editing once they are submitted to the Secretariat. APEC does not support publication of PowerPoint slides. Electronic publication is strongly encouraged – if printed copies are necessary, justify this. The target audiences are those who will be directly using the disseminated results or outputs. Where applicable, mention their occupations, economies, industries, government departments, etc. Websites and databases can be effective tools but APEC does not support the ongoing maintenance and upkeep of websites or databases. If you are producing a website or database, clearly explain who will maintain it and how it will be sustained after APEC funding ends.

- Gender: What steps will the project take to ensure the participation and engagement of both men and women in project activities? How do the project outcomes and the project objective benefit women?   [less than ½ page]

- Women’s full participation in economic activity is critical to the achievement of sustainable economic development in the region. Design steps to support gender equity might include: using gender analysis to design project methodologies and inputs (e.g. surveys); including women in the planning, management, allocation of resources and implementation of a project; taking steps to ensure equitable participation by men and women; making special efforts to disseminate project results to women; and using sex-disaggregated data for project assessments. - Set clear and quantifiable indicators against which gender equity or inclusiveness targets may be measured at the completion of the project. Examples could be female participation rate, number of female/male speakers, etc. - If it is difficult to incorporate women into the project design due to the type of economic sector covered by your project, consider incorporating a gender component through research or community outreach. Inexpensive examples could include inviting female students from a local university to observe workshops or adding a gender related survey question to research that is planned. Benefits of gender programming can include: increasing the involvement of women in the economy and economic institutions; integrating women into global economic networks; strengthening small and medium sized enterprises; and reducing gender inequalities, including through education and training. Wherever possible, give baseline indicators. See Appendix G, Guide on Gender Criteria for APEC Project Proposals of the Guidebook on APEC Projects for further information.

SECTION C:  Project Effectiveness

- 9. Work plan:  Produce a project plan in a table with three columns titled ‘Time’, ‘Tasks’ and ‘Deliverables’ which indicate timelines, outputs and activities, and supporting tasks. Ensure you include:

- Creation of items like agenda, participant lists, project reporting and evaluations.

- How other economies and other parties (like contractors) will be involved.

- Procurement steps, contractor related milestones and deliverables.

- [1-2 pages. Answers can be adapted from the Concept Note]

- Reflecting the order that actions will be performed, describe each step of the project to form a realistic, comprehensive Work Plan. Please use an action matrix (table) to provide a graphical framework for your Work Plan. In the matrix, provide three columns: Time, Task and Deliverables (in that order): For each action addressed in the matrix please include: - Specified dates or date-ranges to indicate the timing of actions. The duration of each task should be realistic given the budget and project duration. Consider the following guidance when defining the duration of specific tasks: - Event preparation including nomination process of participants should commence at least 8 weeks before event date - Pre-event engagement of economies in survey activities or research activities generally take at least 4-8 weeks to finalize - Secretariat payments processing times - Procurement and contracting takes time – ensure you allow 6-8 weeks between the submission of minor contract Terms of Reference for Secretariat approval and the date that a contractor is required to start. RFP timelines can be lengthy and you should work with your PD as soon as possible. - All the Tasks or actions (which might have sub-actions) which may include: - Formation of Steering Committees - Pre-workshop research or survey work - Contracting - Project planning such as organizing event logistics, nominating participants, inviting speakers - Engaging fora, businesses etc. - Monitoring/evaluation (to be described in detail in Q10) - Drafting of reports, followed by circulation and endorsement by forum - Details on involvement in the planning and implementation by: - Various APEC economies - Other APEC fora - Other fora outside APEC: multilateral and regional institutions; sector specific institutions - Business and industry - Related Deliverables for that particular task. Most tasks have a deliverable of some sort. A Deliverable might be an Output, which is the key product or service the project will create, such as a workshop, a research study or a project report. A Deliverable may also be the result of minor tasks, such as workshop preparations, where the resulting deliverable would be an event agenda or a participant list. - Be consistent in the naming of the Deliverables. - Note – the final Deliverable should be the submission of an endorsed Completion Report to the Secretariat, generally within two months after all project activities and financial disbursements have been undertaken. Note that Project Start Date may only begin after proposal approval from the BMC, and not earlier. Generally, Project End Date would be December of the following year after project approval.

- Risks: What risks could impact project implementation and how will they be managed?

[⅛ to 1 page, depending on project nature/complexity]

Risks and risk management strategies need to be described for the project as a whole, and sometimes for specific actions or stages. Explain these strategies in detail if your risks are significant or complicated. Some common risks (and possible management strategies) include: - Low interest in participation or in using results - Possible risk management strategies: ongoing consultation with economies on speakers, strategies and agendas etc; clear communication and “marketing” strategy, survey of demand - Duplication of work of other APEC fora or fora outside APEC - Possible risk management strategies: close consultation with relevant fora; comprehensive research into similar projects; consultation with overseers of precursor projects - Difficulty achieving policy change over the long-term, in target economies - Possible risk management strategies: early and robust engagement of both supportive and oppositional stakeholders; appropriate selection of participants; creating tools/processes to support participants in policy change; follow-up steps to support economies - Delays or untimely preparation - Possible risk management strategies: ongoing consultation, adequate visa application time; early stakeholder/contractor engagement, early adoption of agenda; strict internal deadlines

- Monitoring and Evaluation:

- The project’s success will be measured by the extent to which it has delivered all its planned outcomes, in support of the overall objective of the project. Describe the measures or indicators will you use to monitor the progress of your project, and evaluate if it has delivered all the outcomes.

- Describe the measures/indicators you will use to measure your project’s outputs (e.g. event participation rates, speakers engaged, recommendations made, reports distributed, etc.)

- Describe the measures/indicators you will use to assess if you have achieved your outcomes (e.g. quantitative and qualitative measures of impact, evidence of change, stakeholder feedback, etc. Tip: consider surveying participants at start and end of project to measure the scale of impact)

- How will gender impacts be measured? Ensure you collect sex-disaggregated data.

- How will you collect your data (e.g. surveys, meetings, interviews, peer review, records review)?   [½ page]

Monitoring and evaluation (M&E) is central to project management. Monitoring is the process of ensuring that you are implementing your project according to plan: that is, you are delivering what you set out to do in your BMC-approved Project Proposal. You must always alert the Secretariat to any changes in your work plan, outputs, and outcomes or budget as early as possible. Such changes are called design amendments and must be approved. Evaluation is the process of assessing whether you were successful in achieving your outcomes and in turn, met the project’s objective(s). To do this, you apply the outcome indicators. You should develop tailored indicators that are specific to your project, but many APEC projects will use similar indicators. Please contact the Project Management Unit (PMU@apec.org) if you would like support in developing indicators. A monitoring and evaluation plan describes how you will track progress and measure project success. A monitoring and evaluation plan includes: - Evaluation methods: how will you collect information to show if the project has been a success? Possible methods could include meetings, surveys, interviews, focus group discussions, observation, peer review, records or data review. - Indicators: This includes clear, measurable indicators or observable information at the Output or Outcome level that can be used to determine what has changed because of this project. Some examples are: participant statistics (number, gender, economies, level), stakeholder feedback (comments or grades on how well the project met its objectives), number of recommendations adopted, number of website hits, number of documents distributed, etc. Most indicators can only be measured if you know the starting point or baseline. Indicate if you will have baseline information by the project start date. If you need to collect data, it is easily available and/or inexpensive to collect? Longer-term outcomes measure change over time, so identify long-term indicators and indicate if you will have baseline information on these at the project start date. Some projects use early project stages to collect this information. In this section, indicate how you can observe or measure the project’s impact on women, or men (in female dominated sectors). In developing your plan, remember that APEC requires an annual Monitoring Report for all active projects. APEC also requires a Completion Report for all APEC funded projects. Evaluation of your project using the indicators set in this section should be included in the two reports. Consult the PO Toolkit document “2019: What do I need to know about the new Concept Note and Project Proposal” for an example response.

- Linkages: Describe the involvement of other APEC fora, and relevant other organisations. Include:

- Engagement: How are you engaging other relevant fora, within and outside of APEC?

- Previous work: How does this project build on, yet avoid duplication of, previous or ongoing APEC initiatives, or those of other organisations?

- APEC’s comparative advantage: Why is APEC the best sources of funds for this project?

[¼ to 1 page. Answers may be taken or adapted from the Concept Note]

- You need to describe the involvement of other APEC fora, particularly: - Engagement: Who will you engage and how will you engage them? Are they involved in the planning? Will they be invited to events or will they share in project results? - Previous work: Refer to specific projects or initiatives, where possible. This will take some research, possibly through your APEC committee delegates, consulting other APEC fora, or using the APEC Project Database. Your forum PD may also be able to assist. - Examples of external stakeholders that might be engaged include WTO, WHO, OECD, ASEAN, ADB, trade associations, sectoral bodies, UN agencies, etc. You need to show that you are building off of this work, not duplicating. This will take some research. How can you bring these organisations into your project? - Describe APEC’s comparative advantage: why this project is best undertaken by APEC, rather than by another institution or organisation. How much demonstrated interest is there from APEC economies in this project? Describe how you gauged this interest. You need to demonstrate that the project is of interest to a wide number and variety of APEC economies.

SECTION D:  Project Sustainability

- Sustainability: Describe how the project will continue to have impact after the APEC funding is finished.

- How will beneficiaries be supported to carry forward the results and lessons from the project?

- After project completion, what are the possible next steps to build on its outputs and outcomes? How will you try to ensure these future actions will take place? How will next steps be tracked?

- How will progress on the outcomes and impacts (Question 6) be measured?   [less than 1 page]

After project completion, what are the possible next steps to build on its outputs and outcomes? If you determine that post-implementation actions are critical to sustainability, what do you need to build into this project to ensure these future actions take place? For any possible next steps mentioned, it is crucial to describe the initiatives or actions that will lead to these steps, who will do them and how they will be paid for. Describe how your project will initiate, support and/or track these actions. Possible next steps may include the following: - Maintenance or dissemination of any outputs such as reports, manuals, databases or resources - Follow up workshops / symposiums / meetings - Transfer of knowledge from participants to other colleagues in their home economies - Creation of cooperative network or means of exchanging of ideas - Adoption of best practices / recommendations - Use of results or outcomes in future projects from your fora or APEC or non-APEC fora Indications that sustainability is likely (and that the possible next steps described above will likely take place) may include: - Future funds and/or partnerships that will help carry project objectives forward, or maintain and update project outputs such as websites, databases and research after project completion - Engagement of stakeholders: relationships developed that can carry project objectives forward - Training modules and resources created and made available for wider use - A highly replicable model or event with resources developed for those who wish to replicate it - Participation of beneficiaries/stakeholders of appropriate levels, economies, fora, ministries, industries, etc. - Ability to continue with little future financial input - Inclusion of a stage where participants develop an action plan for future post-project steps - Follow up with beneficiaries through tracer evaluations, progress updates or other post-implementation communication - Demonstrated effectiveness of previous phases of the project

- Project Overseers: Who will manage the project? This includes managing of contractors and specialists. Please include brief details of the PO and any other main point(s) of contact responsible for this project.      [less than ½ page]

Biographies of the main points of contact should highlight their experience in the field, as well as demonstrate their interest in acting as “champion” for this project and its goals. If you intend to directly award a contract to an organization or individual, also provide information about your preferred contractor.

SECTION E:  Project Efficiency

- Budget: Complete the budget and budget notes for the project in the template below. The budget should include calculation assumptions (e.g., unit costs) and self-funding contributions. Please consult the Guidebook on APEC Projects for eligible expenses.

The PO must refer to the Guidebook on APEC Projects in order to develop a project that is compliant with requirements. The Guidebook provides detailed information on APEC budget and payment matters, including those related to: - Labour costs and honoraria - Contracts - Eligibility and entitlements for travel expenses - Publication and distribution costs - Project event costs, hosting costs - Surveys and research expenses - Equipment, etc. When developing your budget: - Research! Make sure you know the costs in the host venue, check flights online, etc. - Make sure your calculations are clear, with units and costs indicated - Your budget lines should match what you have described in proposal questions 1-14, and each item should correspond with an output in your workplan or monitoring & evaluation plan - Add any assumptions in the Notes section to help the Secretariat understand how you decided on a figure - Do not adjust the budget template or add your own fields or lines - Following are some expenses that are not allowable for APEC project funding. They also do not count when calculating self-funding requirements for TILF projects: - Travel expenses for POs - Honoraria for government or international organisation officials - Simultaneous interpretation, or translation of final outputs such as reports - Meals, coffee and tea breaks - Promotional items and gifts (such as banners, briefcases, souvenirs, flowers) - Maintenance costs for websites, databases and other on-line resources (including servers). Development costs may be funded if the PO shows how maintenance costs will be met - Conference registration fees - Local transport costs, including for airport transfers, field trips, or sightseeing - Simultaneous interpretation at project events - Standard office equipment such as computers (including laptops), printers, and cameras In some cases, waivers may be sought for APEC to cover non-allowable expenses. Strong justification is needed. You should ensure your project is as efficient as possible. Some indications of efficiency to keep in mind when designing your project include: - Holding seminars, workshops or symposiums on the margins of other APEC meetings or events to reduce travel, per diem and/or hosting costs - Self-financing from supporters contributing to labour, facilities, travel and other budget areas - Leveraging the results of previous APEC projects, work or findings, or those of other organizations - Disseminating project outputs electronically, rather than publishing hard copies - Making efficient use of consultant or clerical hours - Employing consultants with experience and a good reputation working on similar projects - Using workshop/symposium participants as presenters, enhancing participatory processes - Providing capacity and resources for participants to return to their economies and organize similar events (e.g. training the trainers), or support for implementation of outputs (e.g. for best practices or recommendations) in APEC economies - Demonstrating that reports, websites, research etc. will be used and updated so it remains relevant in the medium to long term - Strategically choosing event locations that leverage local expertise and cuts travel expenses for participants or experts - Obtaining quotes for contractors and services, even when not required to do so by APEC guidelines The tips here may provide some support, but you must consult the Guidebook on APEC Projects as you develop your budget.

APEC Project Itemized Budget

The following is a quick guide only, highlighting a few key guidelines.

It does not represent all APEC expense guidelines or details. Policies may have changed.

Please consult the Guidebook on APEC Projects, Chapter 9: APEC Project Expenses.

| All Figures in USD | # of Units | Unit Rate | APEC Funding | Self-Funding | Notes |
| --- | --- | --- | --- | --- | --- |
| Direct Labour |  |  |  |  |  |
| Speaker’s honorarium (government officials ineligible) | - Maximum of 6 experts per day - Not more than US$1,500 per person per event (NOT on per day basis) - Honorarium is not allowable for: - government officials or international organization officials - PO, contractor or others already engaged on the project |  |  |  |  |
| Translator’s fees | - Translation of material for training, surveys or research is allowable only with strong justification - Simultaneous interpretation requires waiver with strong justification. - Translation of outputs (final reports, etc) into local languages is not allowable without strong justification - In most cases, any translation or interpretation costs must benefit many economies, not just the host or one economy |  |  |  |  |
| Short-term clerical fees | - Tasks should be bundled and contracted to a single contractor, unless strong justification is provided for multiple contracts - Government institutions/employees & international organisations cannot be contracted by APEC unless exceptional circumstances - Staff from the PO’s office cannot be contracted - Check APEC’s contracting requirements, Ch. 12 of the Guidebook: Contracts over $20,000 have tendering requirements |  |  |  |  |
| Contractor (including Contractor’s Secretarial and Researchers’) fees |  |  |  |  |  |
| Travel (Speaker, Experts, Researchers) |  |  |  |  |  |
| - Non-allowable: PO travel expenses |  |  |  |  |  |
| Per diem (incl. accommodation and “75% additional payment”) | - Maximum of 6 experts / day, for days when they have a formal role - Identify the meeting venue (city) - Maximum allowed is 100% Current UN Per Diem Rate x No. of Official Event Days + 1 Arrival Day + One-Off 75% of the UN Per Diem Rate (E.g. 3 day event = 4.75 days, maximum) |  |  |  |  |
| Airfare | - Most direct and economical flight: provide route details, if known - Business class travel only if origin airport to final destination airport exceeds12 hours - Non-member participation: APEC Forum must approve. - Non-allowable: Expenses for preferred airlines or transit stops for non-APEC or personal reasons |  |  |  |  |
| Travel for Participants (from travel-eligible economies only. Active participants only) |  |  |  |  |  |
| - For events in the margins of other APEC meetings: NO airfares funded if attendees are normally funded by their own economy. Per Diems may be funded for project event days. |  |  |  |  |  |
| Per diem (incl. accommodations and “75% additional payment”) | - Per Diem rate is normally same as Speakers/Experts’ rate - Up to 2 travelers from each travel-eligible economy only - Local participants must reside outside venue city to qualify for Per Diem - See “Travel” excerpts above for calculation |  |  |  |  |
| Airfare (restricted economy class) | - Only economy class travel, most direct and economical flight - Up to 2 travelers from each travel-eligible economy only - Provide a breakdown for each economy/region |  |  |  |  |
| Other items |  |  |  |  |  |
| Publication/distribution of report | - Provide a detailed breakdown of the costs - Compilations of presentation slides are not allowed - Electronic publication is encouraged. Justify publishing of hard copies |  |  |  |  |
| Specialized equipment or materials (please describe) | - Not allowed: Standard equipment such as computers, laptops, photocopiers, printers, cameras or ongoing maintenance of project equipment / materials after the project - Make sure there is no duplication of costs ( e.g. is this item also covered under conference room package) |  |  |  |  |
| Photocopying | - Detailed breakdown of costs is requested - Costs must be reasonable with no duplication of publication costs |  |  |  |  |
| Communications | - Amount requested should be reasonable |  |  |  |  |
| Hosting (provide breakdown, e.g., room rental, stationery) | - There should be no hosting cost for research-based projects - No meals (exception possible if hosting package is cheaper) - No field trip costs without strong justification |  |  |  |  |
| Total |  |  |  |  |  |

Budget Note 1: Direct labour: Provide information for APEC-funded positions including general duties, total hours and who will be contracted, if known. (It is not acceptable to contract staff from your own organisation or government employees.)

- Provide any information possible to help the reviewers understand: - What duties any contracted labour will be doing - How many hours they will be contracted for and how they will use those hours - How they will be engaged (tender, direct contract, etc) - Who they are (if known) and how they are qualified to do this work - When contracting any consultants or staff, consult the Implementation section of the Guidebook on APEC Projects (Chapter 12). Note that it is not acceptable to contract staff from your own organization, government employees or employees of international organizations.

Budget Note 2: Waivers: Provide details of any requests for waivers from the normal APEC financial rules, with justifications (e.g. from tendering requirements, for advance payment, simultaneous interpretation payment) in the notes column of the budget table, or below if the waiver requires a detailed explanation.

Requests for waivers need to correspond with the budget. Any exception from APEC funding guidelines needs to be explained and justified under this section. These may include: - Exceptions from contract tendering requirements - Travel costs for government officials or employees of international organizations - Simultaneous interpretation costs - Translation costs of publications - If you are seeking flexibility on APEC contracting procedures, such as direct awarding of a contract, you need to clearly describe why you want this waiver. Also address the value-added to the project of this request and how will you ensure conflict of interest will be avoided.

- Develop your proposal in close cooperation with your forum’s Program Director. They can help with questions and provide support in developing your project design.

From 2018, Relevance also addresses the extent to which a project is aligned with the eligibility criteria and funding priorities of the APEC fund in question, and the extent to which the project will build capacity, particularly for developing APEC economies if the project is funded under the APEC Support Fund (ASF).